## 

## Tesuque Village Community Plan

## Planning Committee Meeting Roadmap 2019

# Phase 1: Committee Review Process and Plan Update Draft: May 2019- August 2019

**Meeting 1: Kick-off and open house information session**

**Meeting 2: Plan Review and Update Process**

Meeting 2 Topic: SGMP Consistency Review and Proposed Changes

**Meeting 3: Plan Review and Update Process**

Meeting 3 Topic: SGMP Consistency Review and Proposed Changes

**Meeting 4: Committee review and approval of draft plan with amendments**

# Phase 2: Public review and adoption process: September 2019- December 2019

**Meeting 5 & 6:** Tesuque Village Community Plan Update Public Review Draft

**Public presentation open house**

Format: 2 Community meetings to present Tesuque Village draft plan to the Tesuque community

**Planning Commission Public Hearing**

**Board of County Commissioners Public Hearings and adoption of Plan**

**2 Public Hearings**